## StoryMapping
[12 empty] | BACKLOG | 3 |  |  |  | 0
[7 empty] | STORIES, TASKS / RELEASE |  |  |  |  | Not started | 4 | 9.756% | Progress subset% all% | 4 | 0
[12 empty] | In progress | 21 | 51.22% | Progress | 21 | 0
[12 empty] | Closed | 8 | 19.51% | Progress | 8 | 0
|  |  |  | Current | [7 empty] | Applied | 5 | 12.2% | 34.21% | 5 | 0
|  |  |  | Week 202114 | [7 empty] | Canceled | 3 | 7.317% |  | 3 | 0
[12 empty] | Suspended | 0 | 0% | 34.21% | 0 | 0
[12 empty] | N/A | 0 | 0% |  | 0 | 0
Target Week | Week of closure or appling | Processed O/N | To be counted | Target Sprint / Week |  | Ref | Type / Module | Story Description | Feature/Project | Priority | Points | Target Date | Date reviewed | Status | Closure or Applied Date | Task/Comment | Team/Contact | LOG
202114 | 202112 | N | 1 | 202114 | 0 | S1 | US | Story 1 description | Feature 1 |  | 5 | 2021-04-01 |  | In progress | 2021-03-20 | + Do something 1 (done at date 1) | Team 1 | + Status changed to 'BACKLOG' (@ 14/07/2017) by AFIF, HASSAN ¦ + Status changed to 'In progress' (@ 14/07/2017) by AFIF, HASSAN ¦ + Status changed to 'Closed' (@ 14/07/2017) by AFIF, HASSAN ¦ + Status changed to 'BACKLOG' (@ 14/07/2017) by AFIF, HASSAN ¦
201713 | 201715 |  | 0 | 201713 |  | S2 | Spike | Story 2 description | Feature 1 | 1 | 8 | 2017-03-30 |  | Canceled | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 1 | + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'N/A' (@ 13/04/2017) + Status changed to 'Suspended' (@ 13/04/2017) + Status changed to 'Not started' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017)
201719 | 201716 | Y | 1 | 201719 |  | S3 | Spike | Story 3 description | Feature 2 |  | 2 | 2017-05-12 |  | Closed | 2017-04-16 | + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Closed' (@ 4/16/2017) ¦
201713 | 201715 | Y | 1 | 201707 |  | S4 | Spike | Story 4 description | Feature 2 |  | 40 | 2017-03-30 | 2017-02-17 | Closed | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Closed' (@ 4/17/2017) ¦ + New reviewed date: '2/17/2017' (@ 4/17/2017) ¦ + New reviewed date: '5/17/2017' (@ 4/17/2017) ¦ + New reviewed date: '17/04/2017' (@ 17/04/2017) ¦ + Status changed to 'Not started' (@ 4/16/2017) ¦ + Status changed to 'Closed' (@ 4/16/2017) ¦ + Status changed to 'In progress' (@ 4/16/2017) ¦ + New reviewed date: '26/04/2017' (@ 13/04/2017) ¦ + Status changed to 'Not started' (@ 13/04/2017) ¦ + Status changed to 'Closed' (@ 13/04/2017) ¦ + Status changed to 'In progress' (@ 13/04/2017) ¦ + Status changed to 'Closed' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'Canceled' (@ 13/04/2017) + Status changed to 'Suspended' (@ 13/04/2017) + Status changed to 'In progress' (@ 13/04/2017) + Status changed to 'Not started' (@ 13/04/2017) + Status changed to 'N/A' (@ 13/04/2017)
201713 | 201713 | Y | 1 | 201713 |  | S5 | Not-US | Story 4 description | Feature 2 |  | 13 | 2017-03-30 |  | Applied | 2017-03-30 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) | Team 2
201713 |  | N | 1 | 201726 | -1 | S6 | Not-US | Story 1 description | Feature 3 |  | 0.5 | 2017-03-27 | 2017-06-25 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 3 | + New reviewed date: '25/06/2017' (@ 19/06/2017) ¦ + New reviewed date: '15/06/2017' (@ 06/06/2017) ¦
201713 | 201716 | Y | 1 | 201713 |  | S7 | Spike | Story 1 description | Feature 4 |  | 20 | 2017-03-27 |  | Closed | 2017-04-17 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Closed' (@ 4/17/2017) ¦ + Status changed to 'Not started' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201726 | -1 | S8 | US | Story 1 description | Feature 1 |  | 2 | 2017-03-31 | 2017-06-30 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 25/04/2017 | Team 1 | + New reviewed date: '30/06/2017' (@ 28/06/2017) by AFIF, HASSAN ¦ + New reviewed date: '22/06/2017' (@ 19/06/2017) ¦ + New reviewed date: '09/06/2017' (@ 06/06/2017) ¦
201713 | 201713 | Y | 1 | 201713 |  | S9 | TS | Story 2 description | Feature 1 | 1 | 5 | 2017-03-30 |  | Closed | 2017-03-30 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) | Team 1
201713 |  | N | 1 | 201729 | -1 | S10 | Epic | Story 4 description | Feature 3 |  | 40 | 2017-03-30 | 2017-07-17 | In progress |  | = Do something 5 @lun 17/07/2017 + Do something 1 (done at date 3) @lun 17/07/2017 + Link tasks list to the story | Team 3 | + New reviewed date: '17/07/2017' (@ 28/06/2017) by AFIF, HASSAN ¦ + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201715 |  | N | 1 | 201716 | -1 | S11 | Epic | Story 4 description | Feature 2 |  | 100 | 2017-04-13 | 2017-04-17 | Not started |  | = Do something 5 + Do something 1 (done at date 4) + Link tasks list to the story | Team 2 | + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201716 |  | N | 1 | 201716 | -1 | S12 | Spike | Story 4 description | Feature 2 |  | 5 | 2017-04-17 |  | In progress |  | X _x Do something 1 (done at date 8) + _/ Do something 1 (done at date 7) = .... Do something 1 (done at date 6) - __ Do something 1 (done at date 5) - - Do something 1 (done at date 4): X X Do something 1 (done at date 3) = => Do something 5 - - Do something 1 (done at date 2) + Link tasks list to the story | Team 2 | + Status changed to 'In progress' (@ 04/07/2017) by AFIF, HASSAN ¦
201733 |  | N | 1 | 201733 | -1 | S13 | US | Story 4 description | Feature 2 |  | 20 | 2017-08-17 |  | Not started |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Not started' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201713 | -1 | S14 | US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201713 |  | Y | 0 |  |  | S15 | Not-US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | BACKLOG |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'BACKLOG' (@ 14/07/2017) by AFIF, HASSAN ¦
201713 | 201713 | Y | 1 | 201713 |  | S16 | TS | Story 1 description | Feature 3 |  | 20 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 3
201713 | 201713 | Y | 1 | 201713 |  | S17 | US | Story 1 description | Feature 1 |  | 40 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201714 |  | N | 1 | 201725 | -1 | S18 | Not-US | Story 1 description | Feature 1 |  | 8 | 2017-04-03 | 2017-06-21 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '21/06/2017' (@ 19/06/2017) ¦ + Status changed to 'In progress' (@ 19/06/2017) ¦
201713 |  | N | 1 | 201726 | -1 | S19 | US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 | 2017-06-30 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '30/06/2017' (@ 19/06/2017) ¦
201727 |  | Y | 0 |  |  | S20 | US | Story 1 description | Feature 3 |  | 20 | 2017-07-07 |  | BACKLOG |  | + Do something 1 (done at date 1) => Do something 2 | Team 3 | + Status changed to 'BACKLOG' (@ 14/07/2017) by AFIF, HASSAN ¦ + Status changed to 'In progress' (@ 22/06/2017) ¦
201713 | 201725 | Y | 1 | 201713 |  | S21 | Epic | Story 1 description | Feature 1 |  | 100 | 2017-03-31 |  | Applied | 2017-06-19 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Applied' (@ 19/06/2017) ¦
201713 | 201713 |  | 0 | 201713 |  | S22 | Epic | Story 1 description | Feature 1 |  | 100 | 2017-03-31 |  | Canceled | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 |  | N | 1 | 201713 | -1 | S23 | US | Story 1 description | Feature 1 |  | 5 | 2017-03-31 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201713 |  | N | 1 | 201716 | -1 | S24 | US | Story 1 description | Feature 3 |  | 5 | 2017-03-31 | 2017-04-20 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 20/04/2017 | Team 3
201713 |  | Y | 0 |  |  | S25 | US | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | BACKLOG |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'BACKLOG' (@ 14/07/2017) by AFIF, HASSAN ¦
201714 | 201713 | Y | 1 | 201714 |  | S26 | Deployment Story | Story 1 description | Feature 1 |  | 40 | 2017-04-04 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201731 |  | N | 1 | 201725 | -1 | S27 | Not-US | Story 1 description | Feature 1 |  | 2 | 2017-07-31 | 2017-06-23 | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + New reviewed date: '23/06/2017' (@ 19/06/2017) ¦
201713 |  | N | 1 | 201726 | -1 | S28 | Not-US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 | 2017-07-01 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 12/04/2017 | Team 1 | + New reviewed date: '01/07/2017' (@ 19/06/2017) ¦ + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201713 |  | N | 1 | 201713 | -1 | S29 | Epic | Story 4 description | Feature 2 |  | 13 | 2017-03-30 |  | In progress |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
201713 | 201713 | Y | 1 | 201713 |  | S30 | Epic | Story 1 description | Feature 1 |  | 20 | 2017-03-31 |  | Closed | 2017-03-31 | + Do something 1 (done at date 1) | Team 1
201713 | 201716 | Y | 1 | 201713 |  | S31 | Deployment Story | Story 1 description | Feature 1 |  | 5 | 2017-03-31 |  | Applied | 2017-04-17 | + Do something 1 (done at date 1) => Do something 2 | Team 1 | + Status changed to 'Applied' (@ 4/17/2017) ¦
201718 |  | Y | 1 | 201718 |  | S32 | Spike | Story 4 description | Feature 2 |  | 100 | 2017-04-30 |  | Applied |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
|  | N | 1 |  | 1 | S33 | US | Story 1 description | Feature 1 |  | 20 |  |  | In progress |  | + New reviewed date: 05/04/2017(@ 12/04/2017) = Do something 2 + Do something 1 (done at date 1) + Link tasks list to the story | Team 1 | + Status changed to 'In progress' (@ 08/07/2017) by AFIF, HASSAN ¦
201719 |  | Y | 0 | 201719 |  | S34 | Deployment Story | Story 3 description | Feature 2 |  | 2 | 2017-05-12 |  |  |  | + Do something 1 (done at date 4) => Do something 5 | Team 2
201713 |  | N | 1 | 201718 | -1 | S35 | Not-US | Story 1 description | Feature 1 |  | 8 | 2017-03-31 | 2017-04-30 | In progress |  | + Do something 1 (done at date 1) => Do something 2 + New reviewed date: 30/04/2017 (@ 12/04/2017) | Team 1
201713 |  | N | 1 | 201716 | -1 | S36 | Deployment Story | Story 1 description | Feature 1 |  | 2 | 2017-03-31 | 2017-04-17 | In progress |  | + New reviewed date: 13/04/2017 (@ 12/04/2017) @ven 31/03/2017 = Do something 2 @ven 31/03/2017 + Do something 1 (done at date 1) @ven 31/03/2017 + Link tasks list to the story | Team 1 | + New reviewed date: '4/17/2017' (@ 4/17/2017) ¦
201718 |  | Y | 1 | 201718 |  | S37 | Non-US | Story 4 description | Feature 2 |  | 100 | 2017-04-30 |  | Applied |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2
201728 |  | N | 1 | 201728 | -1 | S38 | Epic | Story 4 description | Feature 2 |  | 100 | 2017-07-15 |  | Not started |  | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 2 | + Status changed to 'Not started' (@ 22/06/2017) ¦
201713 | 201715 | N | 1 | 201713 | -1 | S39 | Spike | Story 2 description | Feature 1 | 1 | 8 | 2017-03-30 |  | In progress | 2017-04-13 | + Do something 1 (done at date 3) + Do something 1 (done at date 4) => Do something 5 | Team 1 | + Status changed to 'In progress' (@ 18/04/2017) ¦
201726 |  | N | 1 | 201726 | -1 | S40 | Not-US | Story 1 description | Feature 1 |  | 20 | 2017-06-30 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 1
201726 |  | N | 1 | 201726 | -1 | S41 | Deployment Story | Story 1 description | Feature 1 |  | 2 | 2017-06-30 |  | In progress |  |  | Team 1 | + Status changed to 'In progress' (@ 23/06/2017) by AFIF, HASSAN ¦ + Status changed to 'Suspended' (@ 23/06/2017) ¦ by AFIF, HASSAN
201731 |  | N | 1 | 201731 | -1 | S42 | Deployment Story | Story 1 description | Feature 1 |  | 2 | 2017-07-31 |  | In progress |  |  | Team 1
201728 | 201725 |  | 0 | 201728 |  | S43 | Deployment Story | Story 1 description | Feature 1 |  | 2 | 2017-07-15 |  | Canceled | 2017-06-23 |  | Team 1 | + Status changed to 'Canceled' (@ 23/06/2017) ¦
201727 |  | N | 1 | 201727 | -1 | S44 | Deployment Story | Story 1 description | Feature 3 |  | 20 | 2017-07-07 |  | In progress |  | + Do something 1 (done at date 1) => Do something 2 | Team 3
201733 |  | N | 1 | 201733 | -1 | S45 | Deployment Story | Story 4 description | Feature 2 |  | 20 | 2017-08-17 |  | Not started |  |  | Team 2
201739 |  | Y | 0 | 201739 |  | S46 | US | Story 1 description | Feature 3 |  | 5 | 2017-09-30 |  |  |  |  | Team 3 | + New reviewed date: '31/9' (@ 22/06/2017) ¦
201739 |  | Y | 0 | 201739 |  | S47 | Deployment Story | Story 4 description | Feature 2 |  | 20 | 2017-09-30 |  |  |  |  | Team 2
|  | Y | 0 |  |  | S48
|  | Y | 0 |  |  | S49
|  | Y | 0 |  |  | S50
|  | Y | 0 |  |  | S51
|  | Y | 0 |  |  | S52
|  | Y | 0 |  |  | S53
|  | Y | 0 |  |  | S54
|  | Y | 0 |  |  | S55
|  | Y | 0 |  |  | S56
|  | Y | 0 |  |  | S57
|  | Y | 0 |  |  | S58
|  | Y | 0 |  |  | S59
|  | Y | 0 |  |  | S60
|  | Y | 0 |  |  | S61
|  | Y | 0 |  |  | S62
|  | Y | 0 |  |  | S63
|  | Y | 0 |  |  | S64
|  | Y | 0 |  |  | S65
|  | Y | 0 |  |  | S66
|  | Y | 0 |  |  | S67
|  | Y | 0 |  |  | S68
|  | Y | 0 |  |  | S69
|  | Y | 0 |  |  | S70
|  | Y | 0 |  |  | S71
|  | Y | 0 |  |  | S72
|  | Y | 0 |  |  | S73
|  | Y | 0 |  |  | S74
|  | Y | 0 |  |  | S75
|  | Y | 0 |  |  | S76
|  | Y | 0 |  |  | S77
|  | Y | 0 |  |  | S78
|  | Y | 0 |  |  | S79
|  | Y | 0 |  |  | S80
|  | Y | 0 |  |  | S81
|  | Y | 0 |  |  | S82
|  | Y | 0 |  |  | S83
|  | Y | 0 |  |  | S84
|  | Y | 0 |  |  | S85
|  | Y | 0 |  |  | S86
|  | Y | 0 |  |  | S87
|  | Y | 0 |  |  | S88
|  | Y | 0 |  |  | S89
|  | Y | 0 |  |  | S90
|  | Y | 0 |  |  | S91
|  | Y | 0 |  |  | S92
|  | Y | 0 |  |  | S93
|  | Y | 0 |  |  | S94
|  | Y | 0 |  |  | S95
|  | Y | 0 |  |  | S96
|  | Y | 0 |  |  | S97
|  | Y | 0 |  |  | S98
|  | Y | 0 |  |  | S99
|  | Y | 0 |  |  | S100
|  | Y | 0 |  |  | S101
|  | Y | 0 |  |  | S102
|  | Y | 0 |  |  | S103
|  | Y | 0 |  |  | S104
|  | Y | 0 |  |  | S105
|  | Y | 0 |  |  | S106
|  | Y | 0 |  |  | S107
|  | Y | 0 |  |  | S108
|  | Y | 0 |  |  | S109
|  | Y | 0 |  |  | S110
|  | Y | 0 |  |  | S111
|  | Y | 0 |  |  | S112
|  | Y | 0 |  |  | S113
|  | Y | 0 |  |  | S114
|  | Y | 0 |  |  | S115
|  | Y | 0 |  |  | S116
|  | Y | 0 |  |  | S117
|  | Y | 0 |  |  | S118
|  | Y | 0 |  |  | S119
|  | Y | 0 |  |  | S120
|  | Y | 0 |  |  | S121
|  | Y | 0 |  |  | S122
|  | Y | 0 |  |  | S123
|  | Y | 0 |  |  | S124
|  | Y | 0 |  |  | S125
|  | Y | 0 |  |  | S126
|  | Y | 0 |  |  | S127
|  | Y | 0 |  |  | S128
|  | Y | 0 |  |  | S129
|  | Y | 0 |  |  | S130
|  | Y | 0 |  |  | S131
|  | Y | 0 |  |  | S132
|  | Y | 0 |  |  | S133
|  | Y | 0 |  |  | S134
|  | Y | 0 |  |  | S135
|  | Y | 0 |  |  | S136
|  | Y | 0 |  |  | S137
|  | Y | 0 |  |  | S138
|  | Y | 0 |  |  | S139
|  | Y | 0 |  |  | S140
|  | Y | 0 |  |  | S141
|  | Y | 0 |  |  | S142
|  | Y | 0 |  |  | S143
|  | Y | 0 |  |  | S144
|  | Y | 0 |  |  | S145
|  | Y | 0 |  |  | S146
|  | Y | 0 |  |  | S147
|  | Y | 0 |  |  | S148
|  | Y | 0 |  |  | S149
|  | Y | 0 |  |  | S150
|  | Y | 0 |  |  | S151
|  | Y | 0 |  |  | S152
|  | Y | 0 |  |  | S153
|  | Y | 0 |  |  | S154
|  | Y | 0 |  |  | S155
|  | Y | 0 |  |  | S156
|  | Y | 0 |  |  | S157
|  | Y | 0 |  |  | S158
|  | Y | 0 |  |  | S159
|  | Y | 0 |  |  | S160
|  | Y | 0 |  |  | S161
|  | Y | 0 |  |  | S162
|  | Y | 0 |  |  | S163
|  | Y | 0 |  |  | S164
|  | Y | 0 |  |  | S165
|  | Y | 0 |  |  | S166
|  | Y | 0 |  |  | S167
|  | Y | 0 |  |  | S168
|  | Y | 0 |  |  | S169
|  | Y | 0 |  |  | S170
|  | Y | 0 |  |  | S171
|  | Y | 0 |  |  | S172
|  | Y | 0 |  |  | S173
|  | Y | 0 |  |  | S174
|  | Y | 0 |  |  | S175
|  | Y | 0 |  |  | S176
|  | Y | 0 |  |  | S177
|  | Y | 0 |  |  | S178
|  | Y | 0 |  |  | S179
|  | Y | 0 |  |  | S180
|  | Y | 0 |  |  | S181
|  | Y | 0 |  |  | S182
|  | Y | 0 |  |  | S183
|  | Y | 0 |  |  | S184
|  | Y | 0 |  |  | S185
|  | Y | 0 |  |  | S186
|  | Y | 0 |  |  | S187
|  | Y | 0 |  |  | S188
|  | Y | 0 |  |  | S189
|  | Y | 0 |  |  | S190
|  | Y | 0 |  |  | S191
|  | Y | 0 |  |  | S192
|  | Y | 0 |  |  | S193
|  | Y | 0 |  |  | S194
|  | Y | 0 |  |  | S195
|  | Y | 0 |  |  | S196
|  | Y | 0 |  |  | S197
|  | Y | 0 |  |  | S198
|  | Y | 0 |  |  | S199
|  | Y | 0 |  |  | S200
|  | Y | 0 |  |  | S201
|  | Y | 0 |  |  | S202
|  | Y | 0 |  |  | S203
|  | Y | 0 |  |  | S204
|  | Y | 0 |  |  | S205
|  | Y | 0 |  |  | S206
|  | Y | 0 |  |  | S207
|  | Y | 0 |  |  | S208
|  | Y | 0 |  |  | S209
|  | Y | 0 |  |  | S210
|  | Y | 0 |  |  | S211
|  | Y | 0 |  |  | S212
|  | Y | 0 |  |  | S213
|  | Y | 0 |  |  | S214
|  | Y | 0 |  |  | S215
|  | Y | 0 |  |  | S216
|  | Y | 0 |  |  | S217
|  | Y | 0 |  |  | S218
|  | Y | 0 |  |  | S219
|  | Y | 0 |  |  | S220
|  | Y | 0 |  |  | S221
|  | Y | 0 |  |  | S222
|  | Y | 0 |  |  | S223
|  | Y | 0 |  |  | S224
|  | Y | 0 |  |  | S225
|  | Y | 0 |  |  | S226
|  | Y | 0 |  |  | S227
|  | Y | 0 |  |  | S228
|  | Y | 0 |  |  | S229
|  | Y | 0 |  |  | S230
|  | Y | 0 |  |  | S231
|  | Y | 0 |  |  | S232
|  | Y | 0 |  |  | S233
|  | Y | 0 |  |  | S234
|  | Y | 0 |  |  | S235
|  | Y | 0 |  |  | S236
|  | Y | 0 |  |  | S237
|  | Y | 0 |  |  | S238
|  | Y | 0 |  |  | S239
|  | Y | 0 |  |  | S240
|  | Y | 0 |  |  | S241
|  | Y | 0 |  |  | S242
|  | Y | 0 |  |  | S243
|  | Y | 0 |  |  | S244
|  | Y | 0 |  |  | S245
|  | Y | 0 |  |  | S246
|  | Y | 0 |  |  | S247
|  | Y | 0 |  |  | S248
|  | Y | 0 |  |  | S249
|  | Y | 0 |  |  | S250
|  | Y | 0 |  |  | S251
|  | Y | 0 |  |  | S252
|  | Y | 0 |  |  | S253
|  | Y | 0 |  |  | S254
|  | Y | 0 |  |  | S255
|  | Y | 0 |  |  | S256
|  | Y | 0 |  |  | S257
|  | Y | 0 |  |  | S258
|  | Y | 0 |  |  | S259
|  | Y | 0 |  |  | S260
|  | Y | 0 |  |  | S261
|  | Y | 0 |  |  | S262
|  | Y | 0 |  |  | S263
|  | Y | 0 |  |  | S264
|  | Y | 0 |  |  | S265
|  | Y | 0 |  |  | S266
|  | Y | 0 |  |  | S267
|  | Y | 0 |  |  | S268
|  | Y | 0 |  |  | S269
|  | Y | 0 |  |  | S270
|  | Y | 0 |  |  | S271
|  | Y | 0 |  |  | S272
|  | Y | 0 |  |  | S273
|  | Y | 0 |  |  | S274
|  | Y | 0 |  |  | S275
|  | Y | 0 |  |  | S276
|  | Y | 0 |  |  | S277
|  | Y | 0 |  |  | S278
|  | Y | 0 |  |  | S279
|  | Y | 0 |  |  | S280
|  | Y | 0 |  |  | S281
|  | Y | 0 |  |  | S282
|  | Y | 0 |  |  | S283
|  | Y | 0 |  |  | S284
|  | Y | 0 |  |  | S285
|  | Y | 0 |  |  | S286
|  | Y | 0 |  |  | S287
|  | Y | 0 |  |  | S288
|  | Y | 0 |  |  | S289
|  | Y | 0 |  |  | S290
|  | Y | 0 |  |  | S291
|  | Y | 0 |  |  | S292
|  | Y | 0 |  |  | S293
|  | Y | 0 |  |  | S294
|  | Y | 0 |  |  | S295
|  | Y | 0 |  |  | S296
|  | Y | 0 |  |  | S297
|  | Y | 0 |  |  | S298
|  | Y | 0 |  |  | S299
|  | Y | 0 |  |  | S300
|  | Y | 0 |  |  | S301
|  | Y | 0 |  |  | S302
|  | Y | 0 |  |  | S303
|  | Y | 0 |  |  | S304
|  | Y | 0 |  |  | S305
|  | Y | 0 |  |  | S306
|  | Y | 0 |  |  | S307
|  | Y | 0 |  |  | S308
|  | Y | 0 |  |  | S309
|  | Y | 0 |  |  | S310
|  | Y | 0 |  |  | S311
|  | Y | 0 |  |  | S312
|  | Y | 0 |  |  | S313
|  | Y | 0 |  |  | S314
|  | Y | 0 |  |  | S315
|  | Y | 0 |  |  | S316
|  | Y | 0 |  |  | S317
|  | Y | 0 |  |  | S318
|  | Y | 0 |  |  | S319
|  | Y | 0 |  |  | S320
|  | Y | 0 |  |  | S321
|  | Y | 0 |  |  | S322
|  | Y | 0 |  |  | S323
|  | Y | 0 |  |  | S324
|  | Y | 0 |  |  | S325
|  | Y | 0 |  |  | S326
|  | Y | 0 |  |  | S327
|  | Y | 0 |  |  | S328
|  | Y | 0 |  |  | S329
|  | Y | 0 |  |  | S330
|  | Y | 0 |  |  | S331
|  | Y | 0 |  |  | S332
|  | Y | 0 |  |  | S333
|  | Y | 0 |  |  | S334
|  | Y | 0 |  |  | S335
|  | Y | 0 |  |  | S336
|  | Y | 0 |  |  | S337
|  | Y | 0 |  |  | S338
|  | Y | 0 |  |  | S339
|  | Y | 0 |  |  | S340
|  | Y | 0 |  |  | S341
|  | Y | 0 |  |  | S342
|  | Y | 0 |  |  | S343
|  | Y | 0 |  |  | S344
|  | Y | 0 |  |  | S345
|  | Y | 0 |  |  | S346
|  | Y | 0 |  |  | S347
|  | Y | 0 |  |  | S348
|  | Y | 0 |  |  | S349
|  | Y | 0 |  |  | S350
|  | Y | 0 |  |  | S351
|  | Y | 0 |  |  | S352
|  | Y | 0 |  |  | S353
|  | Y | 0 |  |  | S354
|  | Y | 0 |  |  | S355
|  | Y | 0 |  |  | S356
|  | Y | 0 |  |  | S357
|  | Y | 0 |  |  | S358
|  | Y | 0 |  |  | S359
|  | Y | 0 |  |  | S360
|  | Y | 0 |  |  | S361
|  | Y | 0 |  |  | S362
|  | Y | 0 |  |  | S363
|  | Y | 0 |  |  | S364
|  | Y | 0 |  |  | S365
|  | Y | 0 |  |  | S366
|  | Y | 0 |  |  | S367
|  | Y | 0 |  |  | S368
|  | Y | 0 |  |  | S369
|  | Y | 0 |  |  | S370
|  | Y | 0 |  |  | S371
|  | Y | 0 |  |  | S372
|  | Y | 0 |  |  | S373
|  | Y | 0 |  |  | S374
|  | Y | 0 |  |  | S375
|  | Y | 0 |  |  | S376
|  | Y | 0 |  |  | S377
|  | Y | 0 |  |  | S378
|  | Y | 0 |  |  | S379
|  | Y | 0 |  |  | S380
|  | Y | 0 |  |  | S381
|  | Y | 0 |  |  | S382
|  | Y | 0 |  |  | S383
|  | Y | 0 |  |  | S384
|  | Y | 0 |  |  | S385
|  | Y | 0 |  |  | S386
|  | Y | 0 |  |  | S387
|  | Y | 0 |  |  | S388
|  | Y | 0 |  |  | S389
|  | Y | 0 |  |  | S390
|  | Y | 0 |  |  | S391
|  | Y | 0 |  |  | S392
|  | Y | 0 |  |  | S393
|  | Y | 0 |  |  | S394
|  | Y | 0 |  |  | S395
|  | Y | 0 |  |  | S396
|  | Y | 0 |  |  | S397
|  | Y | 0 |  |  | S398
|  | Y | 0 |  |  | S399
|  | Y | 0 |  |  | S400
|  | Y | 0 |  |  | S401
|  | Y | 0 |  |  | S402
|  | Y | 0 |  |  | S403
|  | Y | 0 |  |  | S404
|  | Y | 0 |  |  | S405
|  | Y | 0 |  |  | S406
|  | Y | 0 |  |  | S407
|  | Y | 0 |  |  | S408
|  | Y | 0 |  |  | S409
|  | Y | 0 |  |  | S410
|  | Y | 0 |  |  | S411
|  | Y | 0 |  |  | S412
|  | Y | 0 |  |  | S413
|  | Y | 0 |  |  | S414
|  | Y | 0 |  |  | S415
|  | Y | 0 |  |  | S416
|  | Y | 0 |  |  | S417
|  | Y | 0 |  |  | S418
|  | Y | 0 |  |  | S419
|  | Y | 0 |  |  | S420
|  | Y | 0 |  |  | S421
|  | Y | 0 |  |  | S422
|  | Y | 0 |  |  | S423
|  | Y | 0 |  |  | S424
|  | Y | 0 |  |  | S425
|  | Y | 0 |  |  | S426
|  | Y | 0 |  |  | S427
|  | Y | 0 |  |  | S428
|  | Y | 0 |  |  | S429
|  | Y | 0 |  |  | S430
|  | Y | 0 |  |  | S431
|  | Y | 0 |  |  | S432
|  | Y | 0 |  |  | S433
|  | Y | 0 |  |  | S434
|  | Y | 0 |  |  | S435
|  | Y | 0 |  |  | S436
|  | Y | 0 |  |  | S437
|  | Y | 0 |  |  | S438
|  | Y | 0 |  |  | S439
|  | Y | 0 |  |  | S440
|  | Y | 0 |  |  | S441
|  | Y | 0 |  |  | S442
|  | Y | 0 |  |  | S443
|  | Y | 0 |  |  | S444
|  | Y | 0 |  |  | S445
|  | Y | 0 |  |  | S446
|  | Y | 0 |  |  | S447
|  | Y | 0 |  |  | S448
|  | Y | 0 |  |  | S449
|  | Y | 0 |  |  | S450
|  | Y | 0 |  |  | S451
|  | Y | 0 |  |  | S452
|  | Y | 0 |  |  | S453
|  | Y | 0 |  |  | S454
|  | Y | 0 |  |  | S455
|  | Y | 0 |  |  | S456
|  | Y | 0 |  |  | S457
|  | Y | 0 |  |  | S458
|  | Y | 0 |  |  | S459
|  | Y | 0 |  |  | S460
|  | Y | 0 |  |  | S461
|  | Y | 0 |  |  | S462
|  | Y | 0 |  |  | S463
|  | Y | 0 |  |  | S464
|  | Y | 0 |  |  | S465
|  | Y | 0 |  |  | S466
|  | Y | 0 |  |  | S467
|  | Y | 0 |  |  | S468
|  | Y | 0 |  |  | S469
|  | Y | 0 |  |  | S470
|  | Y | 0 |  |  | S471
|  | Y | 0 |  |  | S472
|  | Y | 0 |  |  | S473
|  | Y | 0 |  |  | S474
|  | Y | 0 |  |  | S475
|  | Y | 0 |  |  | S476
|  | Y | 0 |  |  | S477
|  | Y | 0 |  |  | S478
|  | Y | 0 |  |  | S479
|  | Y | 0 |  |  | S480
|  | Y | 0 |  |  | S481
|  | Y | 0 |  |  | S482
|  | Y | 0 |  |  | S483
|  | Y | 0 |  |  | S484
|  | Y | 0 |  |  | S485
|  | Y | 0 |  |  | S486
|  | Y | 0 |  |  | S487
|  | Y | 0 |  |  | S488
|  | Y | 0 |  |  | S489
|  | Y | 0 |  |  | S490
|  | Y | 0 |  |  | S491
|  | Y | 0 |  |  | S492
|  | Y | 0 |  |  | S493
|  | Y | 0 |  |  | S494
|  | Y | 0 |  |  | S495
|  | Y | 0 |  |  | S496
|  | Y | 0 |  |  | S497
|  | Y | 0 |  |  | S498
|  | Y | 0 |  |  | S499
|  | Y | 0 |  |  | S500
|  | Y | 0 |  |  | S501
|  | Y | 0 |  |  | S502
|  | Y | 0 |  |  | S503
|  | Y | 0 |  |  | S504
|  | Y | 0 |  |  | S505
|  | Y | 0 |  |  | S506
|  | Y | 0 |  |  | S507
|  | Y | 0 |  |  | S508
|  | Y | 0 |  |  | S509
|  | Y | 0 |  |  | S510
|  | Y | 0 |  |  | S511
|  | Y | 0 |  |  | S512
|  | Y | 0 |  |  | S513
|  | Y | 0 |  |  | S514
|  | Y | 0 |  |  | S515
|  | Y | 0 |  |  | S516
|  | Y | 0 |  |  | S517
|  | Y | 0 |  |  | S518
|  | Y | 0 |  |  | S519
|  | Y | 0 |  |  | S520
|  | Y | 0 |  |  | S521
|  | Y | 0 |  |  | S522
|  | Y | 0 |  |  | S523
|  | Y | 0 |  |  | S524
|  | Y | 0 |  |  | S525
|  | Y | 0 |  |  | S526
|  | Y | 0 |  |  | S527
|  | Y | 0 |  |  | S528
|  | Y | 0 |  |  | S529
|  | Y | 0 |  |  | S530
|  | Y | 0 |  |  | S531
|  | Y | 0 |  |  | S532
|  | Y | 0 |  |  | S533
|  | Y | 0 |  |  | S534
|  | Y | 0 |  |  | S535
|  | Y | 0 |  |  | S536
|  | Y | 0 |  |  | S537
|  | Y | 0 |  |  | S538
|  | Y | 0 |  |  | S539
|  | Y | 0 |  |  | S540
|  | Y | 0 |  |  | S541
|  | Y | 0 |  |  | S542
|  | Y | 0 |  |  | S543
|  | Y | 0 |  |  | S544
|  | Y | 0 |  |  | S545
|  | Y | 0 |  |  | S546
|  | Y | 0 |  |  | S547
|  | Y | 0 |  |  | S548
|  | Y | 0 |  |  | S549
|  | Y | 0 |  |  | S550
|  | Y | 0 |  |  | S551
|  | Y | 0 |  |  | S552
|  | Y | 0 |  |  | S553
|  | Y | 0 |  |  | S554
|  | Y | 0 |  |  | S555
|  | Y | 0 |  |  | S556
|  | Y | 0 |  |  | S557
|  | Y | 0 |  |  | S558
|  | Y | 0 |  |  | S559
|  | Y | 0 |  |  | S560
|  | Y | 0 |  |  | S561
|  | Y | 0 |  |  | S562
|  | Y | 0 |  |  | S563
|  | Y | 0 |  |  | S564
|  | Y | 0 |  |  | S565
|  | Y | 0 |  |  | S566
|  | Y | 0 |  |  | S567
|  | Y | 0 |  |  | S568
|  | Y | 0 |  |  | S569
|  | Y | 0 |  |  | S570
|  | Y | 0 |  |  | S571
|  | Y | 0 |  |  | S572
|  | Y | 0 |  |  | S573
|  | Y | 0 |  |  | S574
|  | Y | 0 |  |  | S575
|  | Y | 0 |  |  | S576
|  | Y | 0 |  |  | S577
|  | Y | 0 |  |  | S578
|  | Y | 0 |  |  | S579
|  | Y | 0 |  |  | S580
|  | Y | 0 |  |  | S581
|  | Y | 0 |  |  | S582
|  | Y | 0 |  |  | S583
|  | Y | 0 |  |  | S584
|  | Y | 0 |  |  | S585
|  | Y | 0 |  |  | S586
|  | Y | 0 |  |  | S587
|  | Y | 0 |  |  | S588
|  | Y | 0 |  |  | S589
|  | Y | 0 |  |  | S590
|  | Y | 0 |  |  | S591
|  | Y | 0 |  |  | S592
|  | Y | 0 |  |  | S593
|  | Y | 0 |  |  | S594
|  | Y | 0 |  |  | S595
|  | Y | 0 |  |  | S596
|  | Y | 0 |  |  | S597
|  | Y | 0 |  |  | S598
|  | Y | 0 |  |  | S599
|  | Y | 0 |  |  | S600
|  | Y | 0 |  |  | S601
|  | Y | 0 |  |  | S602
|  | Y | 0 |  |  | S603
|  | Y | 0 |  |  | S604
|  | Y | 0 |  |  | S605
|  | Y | 0 |  |  | S606
|  | Y | 0 |  |  | S607
|  | Y | 0 |  |  | S608
|  | Y | 0 |  |  | S609
|  | Y | 0 |  |  | S610
|  | Y | 0 |  |  | S611
|  | Y | 0 |  |  | S612
|  | Y | 0 |  |  | S613
|  | Y | 0 |  |  | S614
|  | Y | 0 |  |  | S615
|  | Y | 0 |  |  | S616
|  | Y | 0 |  |  | S617
|  | Y | 0 |  |  | S618
|  | Y | 0 |  |  | S619
|  | Y | 0 |  |  | S620
|  | Y | 0 |  |  | S621
|  | Y | 0 |  |  | S622
|  | Y | 0 |  |  | S623
|  | Y | 0 |  |  | S624
|  | Y | 0 |  |  | S625
|  | Y | 0 |  |  | S626
|  | Y | 0 |  |  | S627
|  | Y | 0 |  |  | S628
|  | Y | 0 |  |  | S629
|  | Y | 0 |  |  | S630
|  | Y | 0 |  |  | S631
|  | Y | 0 |  |  | S632
|  | Y | 0 |  |  | S633
|  | Y | 0 |  |  | S634
|  | Y | 0 |  |  | S635
|  | Y | 0 |  |  | S636
|  | Y | 0 |  |  | S637
|  | Y | 0 |  |  | S638
|  | Y | 0 |  |  | S639
|  | Y | 0 |  |  | S640
|  | Y | 0 |  |  | S641
|  | Y | 0 |  |  | S642
|  | Y | 0 |  |  | S643
|  | Y | 0 |  |  | S644
|  | Y | 0 |  |  | S645
|  | Y | 0 |  |  | S646
|  | Y | 0 |  |  | S647
|  | Y | 0 |  |  | S648
|  | Y | 0 |  |  | S649
|  | Y | 0 |  |  | S650
|  | Y | 0 |  |  | S651
|  | Y | 0 |  |  | S652
|  | Y | 0 |  |  | S653
|  | Y | 0 |  |  | S654
|  | Y | 0 |  |  | S655
|  | Y | 0 |  |  | S656
|  | Y | 0 |  |  | S657
|  | Y | 0 |  |  | S658
|  | Y | 0 |  |  | S659
|  | Y | 0 |  |  | S660
|  | Y | 0 |  |  | S661
|  | Y | 0 |  |  | S662
|  | Y | 0 |  |  | S663
|  | Y | 0 |  |  | S664
|  | Y | 0 |  |  | S665
|  | Y | 0 |  |  | S666
|  | Y | 0 |  |  | S667
|  | Y | 0 |  |  | S668
|  | Y | 0 |  |  | S669
|  | Y | 0 |  |  | S670
|  | Y | 0 |  |  | S671
|  | Y | 0 |  |  | S672
|  | Y | 0 |  |  | S673
|  | Y | 0 |  |  | S674
|  | Y | 0 |  |  | S675
|  | Y | 0 |  |  | S676
|  | Y | 0 |  |  | S677
|  | Y | 0 |  |  | S678
|  | Y | 0 |  |  | S679
|  | Y | 0 |  |  | S680
|  | Y | 0 |  |  | S681
|  | Y | 0 |  |  | S682
|  | Y | 0 |  |  | S683
|  | Y | 0 |  |  | S684
|  | Y | 0 |  |  | S685
|  | Y | 0 |  |  | S686
|  | Y | 0 |  |  | S687
|  | Y | 0 |  |  | S688
|  | Y | 0 |  |  | S689
|  | Y | 0 |  |  | S690
|  | Y | 0 |  |  | S691
|  | Y | 0 |  |  | S692
|  | Y | 0 |  |  | S693
|  | Y | 0 |  |  | S694
|  | Y | 0 |  |  | S695
|  | Y | 0 |  |  | S696
|  | Y | 0 |  |  | S697
|  | Y | 0 |  |  | S698
|  | Y | 0 |  |  | S699
|  | Y | 0 |  |  | S700
|  | Y | 0 |  |  | S701
|  | Y | 0 |  |  | S702
|  | Y | 0 |  |  | S703
|  | Y | 0 |  |  | S704
|  | Y | 0 |  |  | S705
|  | Y | 0 |  |  | S706
|  | Y | 0 |  |  | S707
|  | Y | 0 |  |  | S708
|  | Y | 0 |  |  | S709
|  | Y | 0 |  |  | S710
|  | Y | 0 |  |  | S711
|  | Y | 0 |  |  | S712
|  | Y | 0 |  |  | S713
|  | Y | 0 |  |  | S714
|  | Y | 0 |  |  | S715
|  | Y | 0 |  |  | S716
|  | Y | 0 |  |  | S717
|  | Y | 0 |  |  | S718
|  | Y | 0 |  |  | S719
|  | Y | 0 |  |  | S720
|  | Y | 0 |  |  | S721
|  | Y | 0 |  |  | S722
|  | Y | 0 |  |  | S723
|  | Y | 0 |  |  | S724
|  | Y | 0 |  |  | S725
|  | Y | 0 |  |  | S726
|  | Y | 0 |  |  | S727
|  | Y | 0 |  |  | S728
|  | Y | 0 |  |  | S729
|  | Y | 0 |  |  | S730
|  | Y | 0 |  |  | S731
|  | Y | 0 |  |  | S732
|  | Y | 0 |  |  | S733
|  | Y | 0 |  |  | S734
|  | Y | 0 |  |  | S735
|  | Y | 0 |  |  | S736
|  | Y | 0 |  |  | S737
|  | Y | 0 |  |  | S738
|  | Y | 0 |  |  | S739
|  | Y | 0 |  |  | S740
|  | Y | 0 |  |  | S741
|  | Y | 0 |  |  | S742
|  | Y | 0 |  |  | S743
|  | Y | 0 |  |  | S744
|  | Y | 0 |  |  | S745
|  | Y | 0 |  |  | S746
|  | Y | 0 |  |  | S747
|  | Y | 0 |  |  | S748
|  | Y | 0 |  |  | S749
|  | Y | 0 |  |  | S750
|  | Y | 0 |  |  | S751
|  | Y | 0 |  |  | S752
|  | Y | 0 |  |  | S753
|  | Y | 0 |  |  | S754
|  | Y | 0 |  |  | S755
|  | Y | 0 |  |  | S756
|  | Y | 0 |  |  | S757
|  | Y | 0 |  |  | S758
|  | Y | 0 |  |  | S759
|  | Y | 0 |  |  | S760
|  | Y | 0 |  |  | S761
|  | Y | 0 |  |  | S762
|  | Y | 0 |  |  | S763
|  | Y | 0 |  |  | S764
|  | Y | 0 |  |  | S765
|  | Y | 0 |  |  | S766
|  | Y | 0 |  |  | S767
|  | Y | 0 |  |  | S768
|  | Y | 0 |  |  | S769
|  | Y | 0 |  |  | S770
|  | Y | 0 |  |  | S771
|  | Y | 0 |  |  | S772
|  | Y | 0 |  |  | S773
|  | Y | 0 |  |  | S774
|  | Y | 0 |  |  | S775
|  | Y | 0 |  |  | S776
|  | Y | 0 |  |  | S777
|  | Y | 0 |  |  | S778
|  | Y | 0 |  |  | S779
|  | Y | 0 |  |  | S780
|  | Y | 0 |  |  | S781
|  | Y | 0 |  |  | S782
|  | Y | 0 |  |  | S783
|  | Y | 0 |  |  | S784
|  | Y | 0 |  |  | S785
|  | Y | 0 |  |  | S786
|  | Y | 0 |  |  | S787
|  | Y | 0 |  |  | S788
|  | Y | 0 |  |  | S789
|  | Y | 0 |  |  | S790
|  | Y | 0 |  |  | S791
|  | Y | 0 |  |  | S792
|  | Y | 0 |  |  | S793
|  | Y | 0 |  |  | S794
|  | Y | 0 |  |  | S795
|  | Y | 0 |  |  | S796
|  | Y | 0 |  |  | S797
|  | Y | 0 |  |  | S798
|  | Y | 0 |  |  | S799
|  | Y | 0 |  |  | S800
|  | Y | 0 |  |  | S801
|  | Y | 0 |  |  | S802
|  | Y | 0 |  |  | S803
|  | Y | 0 |  |  | S804
|  | Y | 0 |  |  | S805
|  | Y | 0 |  |  | S806
|  | Y | 0 |  |  | S807
|  | Y | 0 |  |  | S808
|  | Y | 0 |  |  | S809
|  | Y | 0 |  |  | S810
|  | Y | 0 |  |  | S811
|  | Y | 0 |  |  | S812
|  | Y | 0 |  |  | S813
|  | Y | 0 |  |  | S814
|  | Y | 0 |  |  | S815
|  | Y | 0 |  |  | S816
|  | Y | 0 |  |  | S817
|  | Y | 0 |  |  | S818
|  | Y | 0 |  |  | S819
|  | Y | 0 |  |  | S820
|  | Y | 0 |  |  | S821
|  | Y | 0 |  |  | S822
|  | Y | 0 |  |  | S823
|  | Y | 0 |  |  | S824
|  | Y | 0 |  |  | S825
|  | Y | 0 |  |  | S826
|  | Y | 0 |  |  | S827
|  | Y | 0 |  |  | S828
|  | Y | 0 |  |  | S829
|  | Y | 0 |  |  | S830
|  | Y | 0 |  |  | S831
|  | Y | 0 |  |  | S832
|  | Y | 0 |  |  | S833
|  | Y | 0 |  |  | S834
|  | Y | 0 |  |  | S835
|  | Y | 0 |  |  | S836
|  | Y | 0 |  |  | S837
|  | Y | 0 |  |  | S838
|  | Y | 0 |  |  | S839
|  | Y | 0 |  |  | S840
|  | Y | 0 |  |  | S841
|  | Y | 0 |  |  | S842
|  | Y | 0 |  |  | S843
|  | Y | 0 |  |  | S844
|  | Y | 0 |  |  | S845
|  | Y | 0 |  |  | S846
|  | Y | 0 |  |  | S847
|  | Y | 0 |  |  | S848
|  | Y | 0 |  |  | S849
|  | Y | 0 |  |  | S850
|  | Y | 0 |  |  | S851
|  | Y | 0 |  |  | S852
|  | Y | 0 |  |  | S853
|  | Y | 0 |  |  | S854
|  | Y | 0 |  |  | S855
|  | Y | 0 |  |  | S856
|  | Y | 0 |  |  | S857
|  | Y | 0 |  |  | S858
|  | Y | 0 |  |  | S859
|  | Y | 0 |  |  | S860
|  | Y | 0 |  |  | S861
|  | Y | 0 |  |  | S862
|  | Y | 0 |  |  | S863
|  | Y | 0 |  |  | S864
|  | Y | 0 |  |  | S865
|  | Y | 0 |  |  | S866
|  | Y | 0 |  |  | S867
|  | Y | 0 |  |  | S868
|  | Y | 0 |  |  | S869
|  | Y | 0 |  |  | S870
|  | Y | 0 |  |  | S871
|  | Y | 0 |  |  | S872
|  | Y | 0 |  |  | S873
|  | Y | 0 |  |  | S874
|  | Y | 0 |  |  | S875
|  | Y | 0 |  |  | S876
|  | Y | 0 |  |  | S877
|  | Y | 0 |  |  | S878
|  | Y | 0 |  |  | S879
|  | Y | 0 |  |  | S880
|  | Y | 0 |  |  | S881
|  | Y | 0 |  |  | S882
|  | Y | 0 |  |  | S883
|  | Y | 0 |  |  | S884
|  | Y | 0 |  |  | S885
|  | Y | 0 |  |  | S886
|  | Y | 0 |  |  | S887
|  | Y | 0 |  |  | S888
|  | Y | 0 |  |  | S889
|  | Y | 0 |  |  | S890
|  | Y | 0 |  |  | S891
|  | Y | 0 |  |  | S892
|  | Y | 0 |  |  | S893
|  | Y | 0 |  |  | S894
|  | Y | 0 |  |  | S895
|  | Y | 0 |  |  | S896
|  | Y | 0 |  |  | S897
|  | Y | 0 |  |  | S898
|  | Y | 0 |  |  | S899
|  | Y | 0 |  |  | S900
|  | Y | 0 |  |  | S901
|  | Y | 0 |  |  | S902
|  | Y | 0 |  |  | S903
|  | Y | 0 |  |  | S904
|  | Y | 0 |  |  | S905
|  | Y | 0 |  |  | S906
|  | Y | 0 |  |  | S907
|  | Y | 0 |  |  | S908
|  | Y | 0 |  |  | S909
|  | Y | 0 |  |  | S910
|  | Y | 0 |  |  | S911
|  | Y | 0 |  |  | S912
|  | Y | 0 |  |  | S913
|  | Y | 0 |  |  | S914
|  | Y | 0 |  |  | S915
|  | Y | 0 |  |  | S916
|  | Y | 0 |  |  | S917
|  | Y | 0 |  |  | S918
|  | Y | 0 |  |  | S919
|  | Y | 0 |  |  | S920
|  | Y | 0 |  |  | S921
|  | Y | 0 |  |  | S922
|  | Y | 0 |  |  | S923
|  | Y | 0 |  |  | S924
|  | Y | 0 |  |  | S925
|  | Y | 0 |  |  | S926
|  | Y | 0 |  |  | S927
|  | Y | 0 |  |  | S928
|  | Y | 0 |  |  | S929
|  | Y | 0 |  |  | S930
|  | Y | 0 |  |  | S931
|  | Y | 0 |  |  | S932
|  | Y | 0 |  |  | S933
|  | Y | 0 |  |  | S934
|  | Y | 0 |  |  | S935
|  | Y | 0 |  |  | S936
|  | Y | 0 |  |  | S937
|  | Y | 0 |  |  | S938
|  | Y | 0 |  |  | S939
|  | Y | 0 |  |  | S940
|  | Y | 0 |  |  | S941
|  | Y | 0 |  |  | S942
|  | Y | 0 |  |  | S943
|  | Y | 0 |  |  | S944
|  | Y | 0 |  |  | S945
|  | Y | 0 |  |  | S946
|  | Y | 0 |  |  | S947
|  | Y | 0 |  |  | S948
|  | Y | 0 |  |  | S949
|  | Y | 0 |  |  | S950
|  | Y | 0 |  |  | S951
|  | Y | 0 |  |  | S952
|  | Y | 0 |  |  | S953
|  | Y | 0 |  |  | S954
|  | Y | 0 |  |  | S955
|  | Y | 0 |  |  | S956
|  | Y | 0 |  |  | S957
|  | Y | 0 |  |  | S958
|  | Y | 0 |  |  | S959
|  | Y | 0 |  |  | S960
|  | Y | 0 |  |  | S961
|  | Y | 0 |  |  | S962
|  | Y | 0 |  |  | S963
|  | Y | 0 |  |  | S964
|  | Y | 0 |  |  | S965
|  | Y | 0 |  |  | S966
|  | Y | 0 |  |  | S967
|  | Y | 0 |  |  | S968
|  | Y | 0 |  |  | S969
|  | Y | 0 |  |  | S970
|  | Y | 0 |  |  | S971
|  | Y | 0 |  |  | S972
|  | Y | 0 |  |  | S973
|  | Y | 0 |  |  | S974
|  | Y | 0 |  |  | S975
|  | Y | 0 |  |  | S976
|  | Y | 0 |  |  | S977
|  | Y | 0 |  |  | S978
|  | Y | 0 |  |  | S979
|  | Y | 0 |  |  | S980
|  | Y | 0 |  |  | S981
|  | Y | 0 |  |  | S982
|  | Y | 0 |  |  | S983
|  | Y | 0 |  |  | S984
|  | Y | 0 |  |  | S985
|  | Y | 0 |  |  | S986
|  | Y | 0 |  |  | S987
|  | Y | 0 |  |  | S988
|  | Y | 0 |  |  | S989
|  | Y | 0 |  |  | S990
|  | Y | 0 |  |  | S991
|  | Y | 0 |  |  | S992
|  | Y | 0 |  |  | S993
|  | Y | 0 |  |  | S994
|  | Y | 0 |  |  | S995
|  | Y | 0 |  |  | S996
|  | Y | 0 |  |  | S997
|  | Y | 0 |  |  | S998
|  | Y | 0 |  |  | S999
Formulas:
Target Week = IF([Target Date]="","",IF(WEEKNUM([Target Date])<10,VALUE(CONCATENATE(YEAR([Target Date]),"0",WEEKNUM([Target Date]))),VALUE(CONCATENATE(YEAR([Target Date]),WEEKNUM([Target Date])))))
Week of closure or appling = IF([Closure or Applied Date]="","",IF(WEEKNUM([Closure or Applied Date])<10,VALUE(CONCATENATE(YEAR([Closure or Applied Date]),"0",WEEKNUM([Closure or Applied Date]))),VALUE(CONCATENATE(YEAR([Closure or Applied Date]),WEEKNUM([Closure or Applied Date])))))
Target Sprint / Week = IFERROR(IF([Status]=Backlog,"",IF([Date reviewed]="",[Target Week],IF(WEEKNUM([Date reviewed])<10,VALUE(CONCATENATE(YEAR([Date reviewed]),"0",WEEKNUM([Date reviewed]))),VALUE(CONCATENATE(YEAR([Date reviewed]),WEEKNUM([Date reviewed])))))),"date? >>")

## ReleaseProgress
MONITORING PROGRESS |  | Current Sprint/Week : |  |  | 202114
Sprint / Week begin following : | 201713
StoryMapping |  | 201713 | 201714 | 201715 | 201716 | 201717 | 201718 | 201719 | 201720 | 201721 | 201722 | 201723 | 201724 | 201725 | 201726 | 201727 | 201728 | 201729 | 201730 | 201731 | 201732 | 201733 | 201734 | 201735 | 201736 | 201737 | 201738 | 201739 | 201740 | 201741 | 201742 | 201743 | 201744 | 201745 | 201746 | 201747 | 201748 | 201749 | 201750 | 201751
| Goal progress | 55.26% | 60.53% | 63.16% | 65.79% | 65.79% | 71.05% | 73.68% | 73.68% | 73.68% | 73.68% | 73.68% | 73.68% | 73.68% | 78.95% | 81.58% | 84.21% | 84.21% | 84.21% | 89.47% | 89.47% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74% | 94.74%
| Actual progress | 15.79% | 15.79% | 18.42% | 26.32% | 26.32% | 26.32% | 26.32% | 26.32% | 26.32% | 26.32% | 26.32% | 26.32% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95% | 28.95%

## Setting
¼ Changing bellow data don't require updating any thing in workbook
| Data Sheet Name: |  | Tasksbook File Name:
| StoryMapping |  | .\SPPT_TPL.xlsx
Logging |  |  | New Release File Name Format:
Enabled |  | Prefix | _newRelease@
|  | Format | yyyymmdd.hhMMss
| Recipients of Snapshot email (To) | Recipients of Snapshot email (Cc)
| Hassan AFIF | AFIF, HASSAN
Display email | Snapshot Email Subject | Snapshot Email Body | Taskbook Email Body
Disabled | SPP snapshot | Hi, Please find enclosed the SPP progress of projects. Best regards, | Hi, Please find enclosed the SPP Tasksbook. Best regards,
| Features/Projects | Team/Contact | Team/To | Team/Cc | Team/Contact constrains
| Feature 1 | Team 1 | team1.1@domain.com;team1.2@domain.com | team1.0@domain.com | Risk 1
| Feature 2 | Team 2 |  |  | Risk 2
| Feature 3 | Team 3 |  |  | Risk 3
| Feature 4 | Team 1 |  |  | …
| Feature 5 | Team 1
| Feature 6 | Team 3
| Feature 7 | Team 4
| Feature 8 | Team 2
| Feature 9 | Team 4
| Feature 10 | Team 1
| Feature 11 | Team 3
| Feature 12 | Team 4
| Feature 13 | Team 2
| Feature 14 | Team 4
| or | NA
| Project 1 | First Last Name 1 |  |  | Busy between time 1 and time 2
| Project 2 | First Last Name 2 |  |  | Don't disturb in day 1 of week
| Project 3 | First Last Name 3 |  |  | …
| Project 4 | First Last Name 4
| Project 5 | First Last Name 5
| Project 6 | First Last Name 6
| Project 7 | First Last Name 7
| Project 8 | First Last Name 8
| Project 9 | First Last Name 9
| Project 10 | First Last Name 10
| Project 11 | First Last Name 11
| Project 12 | First Last Name 12
| Project 13 | First Last Name 13
| Project 14 | First Last Name 14
| Project 15 | First Last Name 15
| Project 16 | First Last Name 16
| Project 17 | First Last Name 17
| Project 18 | First Last Name 18
| Project 19 | First Last Name 19
| Project 20 | First Last Name 20
| Project 21 | First Last Name 21
| Project 22 | First Last Name 22
| Project 23 | First Last Name 23
| Project 24 | First Last Name 24
| Project 25 | First Last Name 25
| Project 26 | First Last Name 26
| Project 27 | First Last Name 27
| Project 28 | First Last Name 28
| Project 29 | First Last Name 29
| Project 30 | First Last Name 30
| Project 31 | First Last Name 31
| Project 32 | First Last Name 32
| Project 33 | First Last Name 33
| Project 34 | First Last Name 34
| Project 35 | First Last Name 35
| Project 36 | First Last Name 36
| Project 37 | First Last Name 37
| Project 38 | First Last Name 38
| Project 39 | First Last Name 39
| Project 40 | First Last Name 40
| Project 41 | First Last Name 41
| Project 42 | First Last Name 42
| Project 43 | First Last Name 43
| Project 44 | First Last Name 44
| Project 45 | First Last Name 45
| Project 46 | First Last Name 46
| Project 47 | First Last Name 47
| Project 48 | First Last Name 48
| Project 49 | First Last Name 49
| Project 50 | First Last Name 50
| Project 51 | First Last Name 51
| Project 52 | First Last Name 52
| Scrum Effort Estimations (points) using Fobonacci serie | Visual only
| 0 | 0
| 0.5 | 0.5
| 1 | 1
| 2 | 2
| 5 | 5
| 8 | 8
| 13 | 13
| 20 | 20
| 40 | 40
| 100 | 100
¼ Changing data bellow requires that you click on [Apply Settings] button in Excel Ribbon tab SPP.
<= Other Color palette to copy/paste format on "Type / Module" range
| Type / Module/Sprint/Version | Description |  | Clearer | Clear | Dark | Darker
| US | User Story: Demonstrable working software that is valuable to the product’s end-users and can be accepted by the team’s Product Owner.
| Not-US | Not a User Story: Demonstrable working software that could not be completed within the confines of a User Story and can be verified by the team as complete.
| Spike | Spike: Information or a Decision that is required to move forward with other items within the Product Backlog and can be summarized and verified by the team. | [copy] / [special paste] if you desire it
Deployment | Deployment Story | Deployment Story: Special Story to define the last week in the Sprint. Without a Story of this type the tool can not find the sprint boundary. | <========
| TS | Technical Story: Rather than a User Story, is a Story with technical goal
| Epic | Epic: Big and Fuzzy Story to be splitted
| Issue | Issue
You can change formating on the following status to be applied later on the wool line of story/task. But only these Font properties can be applied: Bold Color ColorIndex FontStyle Italic Strikethrough Underline Then Execute [Apply Settings.]
Status labels ad color
Not started | Not started
In progress | In progress
BACKLOG | BACKLOG
Closed | Closed
Canceled | Canceled
Suspended | Suspended
Applied | Applied
N/A | N/A
|  | Stories/Tasks begin line | 12
|  | Stories/Tasks end line | 150
Priority
1
2
3
4
5
¼ Data bellow should not to be changed
Computed Sprints List
Sprint 201714
Sprint 201713
Sprint 201719
Sprint 201716
Sprint 201726
Sprint 201731
Sprint 201728
Sprint 201727
Sprint 201733
Sprint 201739
BACK LOG